## PROJECT PARAMETERS
ROBOTINE MANUFACTURING |  |  |  |  | ROBOTINE MANUFACTURING: CONFIDENTIAL
Event management project tracker
Shaded cells are calculated for you. You do not need to enter anything into them.
PROJECT TYPE | ACCOUNT MANAGER | PROJECT MANAGER | STRATEGY MANAGER | DESIGN SPECIALIST | EVENT STAFF | ADMIN STAFF | TOTAL
Event strategy development | 20% | 10% | 60% | 0% | 0% | 10% | 100%
Event planning | 20% | 50% | 10% | 10% | 0% | 10% | 100%
Event design | 20% | 20% | 0% | 50% | 0% | 10% | 100%
Event logistics | 20% | 60% | 0% | 0% | 10% | 10% | 100%
Event staffing | 20% | 10% | 0% | 0% | 60% | 10% | 100%
Event assessment | 20% | 20% | 20% | 20% | 0% | 20% | 100%
Blended rates | 180 | 120 | 150 | 100 | 80 | 60
| ACCOUNT MANAGER | PROJECT MANAGER | STRATEGY MANAGER | DESIGN SPECIALIST | EVENT STAFF | ADMIN STAFF
PLANNED COST | 54000 | 52200 | 24000 | 29000 | 13200 | 9000
ACTUAL COST | 54360 | 51540 | 25650 | 28900 | 13400 | 9060
PLANNED HOURS | 300 | 290 | 133.3333 | 161.1111 | 73.3333 | 50
ACTUAL HOURS | 302 | 286.3333 | 142.5 | 160.5556 | 74.4444 | 50.3333

## PROJECT DETAILS
ROBOTINE MANUFACTURING | [8 empty] | ROBOTINE MANUFACTURING: CONFIDENTIAL
Event management project tracker
PROJECT NAME | PROJECT TYPE | ESTIMATED START | ESTIMATED FINISH | ACTUAL START | ACTUAL FINISH | ESTIMATED WORK | ACTUAL WORK | ESTIMATED DURATION | ACTUAL DURATION | ACCOUNT MANAGER | PROJECT MANAGER | STRATEGY MANAGER | DESIGN SPECIALIST | EVENT STAFF | ADMIN STAFF | ACCOUNT MANAGER | PROJECT MANAGER | STRATEGY MANAGER | DESIGN SPECIALIST | EVENT STAFF | ADMIN STAFF | INFO To add a row, select the bottom-right most cell in the body of the table (not the totals row) and press Tab, or right-click where you want the row inserted and select Insert ¦ Table Rows Above/Below. Be sure all unused rows are deleted, as the PROJECT TOTALS PivotTable will use all of the tables cells, and otherwise would give erroneous results.
Project 1 | Event strategy development | 2023-06-09 | 2023-08-07 | 2023-06-29 | 2023-09-03 | 200 | 220 | 58 | 64 | 1919-09-17 | 1906-07-27 | 1949-04-12 | 0 | 0 | 1903-04-14 | 1921-09-06 | 1907-03-24 | 1954-03-17 | 0 | 0 | 1903-08-12
Project 2 | Event planning | 2024-06-25 | 2024-07-27 | 2023-07-15 | 2024-08-25 | 400 | 390 | 32 | 400 | 1939-06-04 | 1965-09-15 | 1916-06-04 | 1910-12-13 | 0 | 1906-07-27 | 1938-06-09 | 1964-01-24 | 1916-01-06 | 1910-09-04 | 0 | 1906-05-28
Project 3 | Event design | 2025-07-12 | 2025-09-19 | 2025-08-07 | 2025-10-25 | 500 | 500 | 67 | 78 | 1949-04-12 | 1932-11-07 | 0 | 1968-06-11 | 0 | 1908-03-18 | 1949-04-12 | 1932-11-07 | 0 | 1968-06-11 | 0 | 1908-03-18
Project 4 | Event logistics | 2026-07-30 | 2026-09-28 | 2026-09-14 | 2026-11-13 | 150 | 145 | 58 | 59 | 1914-10-13 | 1929-07-26 | 0 | 0 | 1903-04-14 | 1902-06-18 | 1914-04-16 | 1928-07-31 | 0 | 0 | 1903-03-05 | 1902-05-19
Project 5 | Event staffing | 2027-08-11 | 2027-08-21 | 2027-09-14 | 2027-09-25 | 250 | 255 | 10 | 11 | 1924-08-21 | 1908-03-18 | 0 | 0 | 1932-11-07 | 1904-02-08 | 1925-02-17 | 1908-05-17 | 0 | 0 | 1933-07-05 | 1904-03-09
TOTAL | [5 empty] | 1500 | 1510 | 225 | 612

## PROJECT TOTALS
ROBOTINE MANUFACTURING | [11 empty] | ROBOTINE MANUFACTURING: CONFIDENTIAL
Event Management Project Tracker
PROJECT NAME | ACCOUNT MANAGER ESTIMATE | PROJECT MANAGER ESTIMATE | STRATEGY MANAGER ESTIMATE | DESIGN SPECIALIST ESTIMATE | EVENT STAFF ESTIMATE | ADMIN STAFF ESTIMATE | ACCOUNT MANAGER ACTUAL | PROJECT MANAGER ACTUAL | STRATEGY MANAGER ACTUAL | DESIGN SPECIALIST ACTUAL | EVENT STAFF ACTUAL | ADMIN STAFF ACTUAL | INFO This PivotTable will not refresh automatically. To refresh it, go to Data Tab in the ribbon and click Refresh All.
Project 1 | 7200 | 2400 | 18000 | 0 | 0 | 1200 | 7920 | 2640 | 19800 | 0 | 0 | 1320
Project 2 | 14400 | 24000 | 6000 | 4000 | 0 | 2400 | 14040 | 23400 | 5850 | 3900 | 0 | 2340
Project 3 | 18000 | 12000 | 0 | 25000 | 0 | 3000 | 18000 | 12000 | 0 | 25000 | 0 | 3000
Project 4 | 5400 | 10800 | 0 | 0 | 1200 | 900 | 5220 | 10440 | 0 | 0 | 1160 | 870
Project 5 | 9000 | 3000 | 0 | 0 | 12000 | 1500 | 9180 | 3060 | 0 | 0 | 12240 | 1530
Grand Total | 54000 | 52200 | 24000 | 29000 | 13200 | 9000 | 54360 | 51540 | 25650 | 28900 | 13400 | 9060